## Issue Tracker
Issue Number | Issue Description | Severity | Priority | Status | Datetime Resolved
1 | Login page: Navigation redirect to dashboard on login is not working. Redirect taking place, but still ending up on the login page. | Low | Low | Resolved | 2024-11-14 10:52
2 | Create New Announcement Modal Responsiveness: Top of modal is covered by the header resulting from sidebar transformation when device is small. Modal is too tall and needs to have overflow adjusted and scrollbar added. | Medium | Low | Resolved | 2024-11-14 10:03
3 | Announcement Modal Responsiveness Mobile: Top of modal is covered by the header resulting from sidebar transformation when device is small | Medium | Low | Resolved | 2024-11-14 10:07
4 | Announcement Modal Responsiveness Tablet: Top of modal is covered by the header resulting from sidebar transformation when device is small | Medium | Low | Resolved | 2024-11-14 22:50
5 | Change Password Modal not progressing and letting person change password or move on | High | High | Resolved | 2024-11-14 14:25
6 | Update Board Members Modal Responsiveness Mobile: Unable to see the End Role buttons when the screen is small. Table collapses without a scrollbar or ability to see everything | Medium | Medium | Resolved | 2024-11-14 17:07
7 | Board Member Update: Cant update a person if there end date was the same days date. Like if they switched roles. Cant add them back to the same role because of table. | High | High | Resolved | 2024-11-14 13:34
8 | Document sorting caused error for documents with no title of date, | Medium | Medium | Resolved | 2024-11-14 20:49
9 | Document download in Document Modal on the Document page was not actually downloading the file. The code for it had be slightly overwritten and was no longer functional. | High | High | Resolved | 2024-11-14 21:51
10 | Login Page: Incorrect passwords to do not have a message that is appearing to say so | Medium | Medium | Resolved | 2024-11-15 08:25
11 | Messages: Replies not lining up with the correct parent message. Parent Message ID wrong? | High | Medium | Resolved | 2024-11-15 09:41
12 | Create New Survey Responsiveness: Top of modal is covered by the header resulting from sidebar transformation when device is small. Modal is too tall and needs to have overflow adjusted and scrollbar added. | Medium | Low | Resolved | 2024-11-15 13:15
13 | Survey Results Modal Responsiveness: Top of modal is covered by the header resulting from sidebar transformation when device is small. Modal is too tall and needs to have overflow adjusted and scrollbar added. | Medium | Low | Resolved | 2024-11-15 13:26
14 | Manage Assessments Modal needs validation of user input for the amount | Medium | Medium | Resolved | 2024-11-27 14:13
15 | Manage Assessments Modal needs validation of user input for the year | Medium | Medium | Resolved | 2024-11-27 14:13
16 | Registration Modal, was not repsonding to registration attempt. Replaced the old apiServie call with authService call | High | High | Resolved | 2024-11-27 15:21
17 | Registration Modal. Inputs needed validation. Email, phone, passwords and comparison | Medium | Medium | Resolved | 2024-11-27 15:21
18 | Registration Modal. Needs to navigate immediately to login on success and give user feedback | Low | Low | Resolved | 11/27/2024 6:254:00 PM
19 | Issue Violation Modal. Dark mode review text is not visible | Low | Low | Resolved | 2024-11-27 15:34
20 | Charge Details was trying to show both assessment and violation data at the same time which is impossible | Medium | Medium | Resolved | 2024-11-27 15:40
21 | Card Management Modal, cant delete a card | High | High | Resolved | 2024-11-30 22:08

## Complete
Format: HOA-[Module]-[Type]-[Component]-[Number]
Module Code | Type Code | Component Code
ACC: Accessibility | ACC: Accessibility Test | ASS: Assessment Modal
ACT:Account Management | AT: Acceptance Test | BDASH: Board Dashboard
ANT: Announcements | IT: Integration Test | CARD: Card Component
ASS: Assessment | PT: Performance Test | DASH: Dashboard
AUTH: Authentication | RESP: Responsive Test | FORM: Form Component
BRD: Board Management | SEC: Security Test | LOG: Login Component
DOC: Document Management | ST: System Test | MOD: Modal
INT: Integration | UT: Unit Test | NAV: Navigation
MSG: Messaging System |  | REG: Registration Modal
PAY: Payment System |  | TABLE: Table Component
PERF: Performance |  | VIO: Violation Modal
RES: Responsive Design
SEC: Security
SUR: Surveys
USR: User Management
VIO: Violation
Account | Announcement | Authentication | Board Management | Document | Message | Payment | Survey | User | Assessment | Violation | Intergration |  |  |  | Responsivness | Security | System
HOA-ACT-UT-DASH-001 | HOA-ANT-UT-PAGE-001 | HOA-AUTH-UT-LOG-001 | HOA-BRD-UT-BDASH-001 | HOA-DOC-UT-PAGE-001 | HOA-MSG-UT-PAGE-001 | HOA-PAY-UT-PAGE-001 | HOA-SUR-UT-PAGE-001 | HOA-USR-UT-OWN-001 | HOA-ASS-UT-ISS-001 | HOA-VIO-UT-ISS-001 | HOA-INT-IT-AUTH-001 | HOA-INT-IT-MSG-001 | HOA-INT-IT-SRV-001 | HOA-INT-IT-VIO-001 | HOA-RES-LAY-001 | HOA-SEC-AUTH-001 | HOA-SYS-INT-001
HOA-ACT-UT-DASH-002 | HOA-ANT-UT-PAGE-002 | HOA-AUTH-UT-LOG-002 | HOA-BRD-UT-BDASH-002 | HOA-DOC-UT-PAGE-002 | HOA-MSG-UT-PAGE-002 | HOA-PAY-UT-PAGE-002 | HOA-SUR-UT-PAGE-002 | HOA-USR-UT-OWN-002 | HOA-ASS-UT-ISS-002 | HOA-VIO-UT-ISS-002 | HOA-INT-IT-AUTH-002 | HOA-INT-IT-MSG-002 | HOA-INT-IT-SRV-002 | HOA-INT-IT-VIO-002 | HOA-RES-LAY-002 | HOA-SEC-AUTH-002 | HOA-SYS-INT-002
HOA-ACT-IT-DASH-001 | HOA-ANT-IT-PAGE-001 | HOA-AUTH-IT-LOG-001 | HOA-BRD-IT-BDASH-001 | HOA-DOC-UT-PAGE-003 | HOA-MSG-IT-PAGE-001 | HOA-PAY-UT-PAGE-003 | HOA-SUR-IT-PAGE-001 | HOA-USR-UT-OWN-003 | HOA-ASS-UT-ISS-003 | HOA-VIO-IT-ISS-001 | HOA-INT-IT-AUTH-003 | HOA-INT-IT-MSG-003 | HOA-INT-IT-SRV-003 | HOA-INT-IT-VIO-003 | HOA-RES-LAY-003 | HOA-SEC-AUTH-003 | HOA-SYS-INT-003
HOA-ACT-RESP-DASH-001 | HOA-ANT-RESP-PAGE-001 | HOA-AUTH-SEC-LOG-001 | HOA-BRD-RESP-BDASH-001 | HOA-DOC-IT-PAGE-001 | HOA-MSG-RESP-PAGE-001 | HOA-PAY-IT-PAGE-001 | HOA-SUR-RESP-PAGE-001 | HOA-USR-IT-OWN-001 | HOA-ASS-UT-ISS-004 | HOA-VIO-RESP-ISS-001 | HOA-INT-IT-AUTH-004 | HOA-INT-IT-MSG-004 | HOA-INT-IT-SRV-004 | HOA-INT-IT-VIO-004 | HOA-RES-LAY-004 | HOA-SEC-AUTH-004 | HOA-SYS-INT-004
HOA-ACT-RESP-DASH-002 | HOA-ANT-RESP-PAGE-002 | HOA-AUTH-RESP-LOG-001 | HOA-BRD-RESP-BDASH-002 | HOA-DOC-RESP-PAGE-001 | HOA-MSG-RESP-PAGE-002 | HOA-PAY-RESP-PAGE-001 | HOA-SUR-RESP-PAGE-002 | HOA-USR-RESP-OWN-001 | HOA-ASS-IT-ISS-001 | HOA-VIO-RESP-ISS-002 | HOA-INT-IT-AUTH-005 | HOA-INT-IT-MSG-005 | HOA-INT-IT-SRV-005 | HOA-INT-IT-VIO-005 | HOA-RES-LAY-005 | HOA-SEC-DATA-001 | HOA-SYS-INT-005
HOA-ACT-RESP-DASH-003 | HOA-ANT-RESP-PAGE-003 | HOA-AUTH-RESP-LOG-002 | HOA-BRD-RESP-BDASH-003 | HOA-DOC-RESP-PAGE-002 | HOA-MSG-RESP-PAGE-003 | HOA-PAY-RESP-PAGE-002 | HOA-SUR-RESP-PAGE-003 | HOA-USR-RESP-OWN-002 | HOA-ASS-IT-ISS-002 | HOA-VIO-RESP-ISS-003 | HOA-INT-IT-AUTH-006 | HOA-INT-IT-MSG-006 | HOA-INT-IT-SRV-006 | HOA-INT-IT-VIO-006 | HOA-RES-MOD-001 | HOA-SEC-DATA-002 | HOA-SYS-BRW-001
HOA-ACT-ACC-DASH-001 | HOA-ANT-ACC-PAGE-001 | HOA-AUTH-RESP-LOG-003 | HOA-BRD-ACC-BDASH-001 | HOA-DOC-RESP-PAGE-003 | HOA-MSG-ACC-PAGE-001 | HOA-PAY-RESP-PAGE-003 | HOA-SUR-ACC-PAGE-001 | HOA-USR-RESP-OWN-003 | HOA-ASS-RESP-ISS-001 | HOA-VIO-ACC-ISS-001 | HOA-INT-IT-AUTH-007 | HOA-INT-IT-MSG-007 | HOA-INT-IT-SRV-007 | HOA-INT-IT-VIO-007 | HOA-RES-MOD-002 | HOA-SEC-DATA-003 | HOA-SYS-BRW-002
HOA-ACT-UT-NEW-001 | HOA-ANT-UT-CRT-001 | HOA-AUTH-UT-REG-001 | HOA-BRD-UT-BSET-001 | HOA-DOC-UT-UPL-001 | HOA-MSG-UT-NEW-001 | HOA-PAY-ACC-PAGE-001 | HOA-SUR-UT-CRT-001 | HOA-USR-ACC-OWN-001 | HOA-ASS-RESP-ISS-002 | HOA-VIO-UT-UPD-001 | HOA-INT-IT-AUTH-008 | HOA-INT-IT-MSG-008 | HOA-INT-IT-SRV-008 | HOA-INT-IT-VIO-008 | HOA-RES-MOD-003 | HOA-SEC-DATA-004 | HOA-SYS-BRW-003
HOA-ACT-UT-NEW-002 | HOA-ANT-UT-CRT-002 | HOA-AUTH-UT-REG-002 | HOA-BRD-UT-BSET-002 | HOA-DOC-UT-UPL-002 | HOA-MSG-UT-NEW-002 | HOA-PAY-UT-PAY-001 | HOA-SUR-UT-CRT-002 | HOA-USR-UT-PROF-001 | HOA-ASS-RESP-ISS-003 | HOA-VIO-UT-UPD-002 | HOA-INT-IT-AUTH-009 | HOA-INT-IT-MSG-009 | HOA-INT-IT-SRV-009 | HOA-INT-IT-VIO-009 | HOA-RES-MOD-004 | HOA-SEC-API-001 | HOA-SYS-BRW-004
HOA-ACT-UT-NEW-003 | HOA-ANT-UT-CRT-003 | HOA-AUTH-IT-REG-001 | HOA-BRD-IT-BSET-001 | HOA-DOC-UT-UPL-003 | HOA-MSG-IT-NEW-001 | HOA-PAY-UT-PAY-002 | HOA-SUR-IT-CRT-001 | HOA-USR-UT-PROF-002 | HOA-ASS-ACC-ISS-001 | HOA-VIO-IT-UPD-001 | HOA-INT-IT-AUTH-010 | HOA-INT-IT-MSG-010 | HOA-INT-IT-SRV-010 | HOA-INT-IT-VIO-010 | HOA-RES-MOD-005 | HOA-SEC-API-002 | HOA-SYS-BRW-005
HOA-ACT-IT-NEW-001 | HOA-ANT-IT-CRT-001 | HOA-AUTH-RESP-REG-001 | HOA-BRD-RESP-BSET-001 | HOA-DOC-IT-UPL-001 | HOA-MSG-RESP-NEW-001 | HOA-PAY-IT-PAY-001 | HOA-SUR-RESP-CRT-001 | HOA-USR-IT-PROF-001 | HOA-ASS-UT-MNG-001 | HOA-VIO-RESP-UPD-001 | HOA-INT-IT-PAY-001 | HOA-INT-IT-BRD-001 | HOA-INT-IT-PRF-001 | HOA-INT-IT-VIO-011 | HOA-RES-CONT-001 | HOA-SEC-API-003
HOA-ACT-RESP-NEW-001 | HOA-ANT-RESP-CRT-001 | HOA-AUTH-RESP-REG-002 | HOA-BRD-RESP-BSET-002 | HOA-DOC-RESP-UPL-001 | HOA-MSG-RESP-NEW-002 | HOA-PAY-RESP-PAY-001 | HOA-SUR-RESP-CRT-002 | HOA-USR-RESP-PROF-001 | HOA-ASS-UT-MNG-002 | HOA-VIO-RESP-UPD-002 | HOA-INT-IT-PAY-002 | HOA-INT-IT-BRD-002 | HOA-INT-IT-PRF-002 | HOA-INT-IT-VIO-012 | HOA-RES-CONT-002 | HOA-SEC-API-004
HOA-ACT-RESP-NEW-002 | HOA-ANT-RESP-CRT-002 | HOA-AUTH-RESP-REG-003 | HOA-BRD-RESP-BSET-003 | HOA-DOC-RESP-UPL-002 | HOA-MSG-RESP-NEW-003 | HOA-PAY-RESP-PAY-002 | HOA-SUR-RESP-CRT-003 | HOA-USR-RESP-PROF-002 | HOA-ASS-UT-MNG-003 | HOA-VIO-RESP-UPD-003 | HOA-INT-IT-PAY-003 | HOA-INT-IT-BRD-003 | HOA-INT-IT-PRF-003 | HOA-INT-IT-VIO-013 | HOA-RES-CONT-003
HOA-ACT-RESP-NEW-003 | HOA-ANT-RESP-CRT-003 | HOA-AUTH-ACC-REG-001 | HOA-BRD-ACC-BSET-001 | HOA-DOC-RESP-UPL-003 | HOA-MSG-ACC-NEW-001 | HOA-PAY-RESP-PAY-003 | HOA-SUR-ACC-CRT-001 | HOA-USR-RESP-PROF-003 | HOA-ASS-UT-MNG-004 | HOA-VIO-ACC-UPD-001 | HOA-INT-IT-PAY-004 | HOA-INT-IT-BRD-004 | HOA-INT-IT-PRF-004 | HOA-INT-IT-VIO-014 | HOA-RES-CONT-004
HOA-ACT-ACC-NEW-001 | HOA-ANT-ACC-CRT-001 | HOA-AUTH-UT-PASS-001 | HOA-BRD-UT-UPD-001 | HOA-DOC-ACC-UPL-001 | HOA-MSG-UT-DTL-001 | HOA-PAY-ACC-PAY-001 | HOA-SUR-UT-RES-001 | HOA-USR-ACC-PROF-001 | HOA-ASS-IT-MNG-001 |  | HOA-INT-IT-PAY-005 | HOA-INT-IT-BRD-005 | HOA-INT-IT-PRF-005 | HOA-INT-IT-VIO-015 | HOA-RES-CONT-005
| HOA-ANT-UT-CAR-001 | HOA-AUTH-IT-PASS-001 | HOA-BRD-UT-UPD-002 | HOA-DOC-UT-CARD-001 | HOA-MSG-UT-DTL-002 | HOA-PAY-UT-CARD-001 | HOA-SUR-IT-RES-001 | HOA-USR-UT-CONT-001 | HOA-ASS-IT-MNG-002 |  | HOA-INT-IT-PAY-006 | HOA-INT-IT-BRD-006 | HOA-INT-IT-PRF-006
| HOA-ANT-UT-CAR-002 | HOA-AUTH-RESP-PASS-001 | HOA-BRD-IT-UPD-001 | HOA-DOC-UT-CARD-002 | HOA-MSG-IT-DTL-001 | HOA-PAY-UT-CARD-002 | HOA-SUR-RESP-RES-001 | HOA-USR-UT-CONT-002 | HOA-ASS-RESP-MNG-001 |  | HOA-INT-IT-PAY-007 | HOA-INT-IT-BRD-007 | HOA-INT-IT-PRF-007
| HOA-ANT-UT-CAL-001 | HOA-AUTH-RESP-PASS-002 | HOA-BRD-RESP-UPD-001 | HOA-DOC-RESP-CARD-001 | HOA-MSG-RESP-DTL-001 | HOA-PAY-UT-CARD-003 | HOA-SUR-RESP-RES-002 | HOA-USR-IT-CONT-001 | HOA-ASS-RESP-MNG-002 |  | HOA-INT-IT-PAY-008 | HOA-INT-IT-BRD-008 | HOA-INT-IT-PRF-008
| HOA-ANT-RESP-CAR-001 | HOA-AUTH-RESP-PASS-003 | HOA-BRD-RESP-UPD-002 | HOA-DOC-RESP-CARD-002 | HOA-MSG-RESP-DTL-002 | HOA-PAY-IT-CARD-001 | HOA-SUR-RESP-RES-003 | HOA-USR-RESP-CONT-001 | HOA-ASS-RESP-MNG-003 |  | HOA-INT-IT-PAY-009 | HOA-INT-IT-BRD-009 | HOA-INT-IT-PRF-009
| HOA-ANT-RESP-CAR-002 | HOA-AUTH-ACC-PASS-001 | HOA-BRD-RESP-UPD-003 | HOA-DOC-RESP-CARD-003 | HOA-MSG-RESP-DTL-003 | HOA-PAY-RESP-CARD-001 | HOA-SUR-ACC-RES-001 | HOA-USR-RESP-CONT-002 | HOA-ASS-ACC-MNG-001 |  | HOA-INT-IT-PAY-010 | HOA-INT-IT-BRD-010 | HOA-INT-IT-PRF-010
| HOA-ANT-RESP-CAR-003 |  | HOA-BRD-ACC-UPD-001 | HOA-DOC-ACC-CARD-001 | HOA-MSG-ACC-DTL-001 | HOA-PAY-RESP-CARD-002 | HOA-SUR-UT-COM-001 | HOA-USR-RESP-CONT-003 |  |  | HOA-INT-IT-DOC-001 | HOA-INT-IT-ANC-001 | HOA-INT-IT-ASS-001
| HOA-ANT-ACC-CAR-001 |  |  |  |  | HOA-PAY-RESP-CARD-003 | HOA-SUR-IT-COM-001 | HOA-USR-ACC-CONT-001 |  |  | HOA-INT-IT-DOC-002 | HOA-INT-IT-ANC-002 | HOA-INT-IT-ASS-002
[6 empty] | HOA-PAY-UT-HIST-001 | HOA-SUR-RESP-COM-001 | HOA-NOT-UT-PREF-001 |  |  | HOA-INT-IT-DOC-003 | HOA-INT-IT-ANC-003 | HOA-INT-IT-ASS-003
[6 empty] | HOA-PAY-UT-HIST-002 | HOA-SUR-RESP-COM-002 | HOA-NOT-UT-PREF-002 |  |  | HOA-INT-IT-DOC-004 | HOA-INT-IT-ANC-004 | HOA-INT-IT-ASS-004
[6 empty] | HOA-PAY-IT-HIST-001 | HOA-SUR-RESP-COM-003 | HOA-NOT-UT-PREF-003 |  |  | HOA-INT-IT-DOC-005 | HOA-INT-IT-ANC-005 | HOA-INT-IT-ASS-005
[6 empty] | HOA-PAY-RESP-HIST-001 | HOA-SUR-ACC-COM-001 | HOA-NOT-IT-PREF-001 |  |  | HOA-INT-IT-DOC-006 | HOA-INT-IT-ANC-006 | HOA-INT-IT-ASS-006
[6 empty] | HOA-PAY-RESP-HIST-002 |  | HOA-NOT-RESP-PREF-001 |  |  | HOA-INT-IT-DOC-007 | HOA-INT-IT-ANC-007 | HOA-INT-IT-ASS-007
[6 empty] | HOA-PAY-RESP-HIST-003 |  | HOA-NOT-RESP-PREF-002 |  |  | HOA-INT-IT-DOC-008 | HOA-INT-IT-ANC-008 | HOA-INT-IT-ASS-008
[6 empty] | HOA-PAY-ACC-HIST-001 |  | HOA-NOT-RESP-PREF-003 |  |  | HOA-INT-IT-DOC-009 | HOA-INT-IT-ANC-009 | HOA-INT-IT-ASS-009
[8 empty] | HOA-NOT-ACC-PREF-001 |  |  | HOA-INT-IT-DOC-010 | HOA-INT-IT-ANC-010 | HOA-INT-IT-ASS-010

## Account
Property Dashboard (Dashboard.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ACC-UT-DASH-001 | Account Info | Info Display | Test account information display | High | Dashboard.js | Testing Complete | 2024-11-13 11:01 | Manual Inspection, Accouunt Info and Recent Charges visible and updated
HOA-ACC-UT-DASH-002 | Quick Links | Link Function | Test quick link navigation | High | Dashboard.js | Testing Complete | 2024-11-13 11:16 | Manual Inspection, directs user to the correct pages
HOA-ACC-IT-DASH-001 | Data Load | Initial Load | Test dashboard data fetching | High | Dashboard.js, apiService.js | Testing Complete | 2024-11-13 11:17 | Manual Inspection, Loads account info and recent updates
HOA-ACC-RESP-DASH-001 | Dashboard Mobile | Mobile Layout < 768px | Test responsive layout | High | Dashboard.js | Testing Complete | 2024-11-13 11:19 | Manual Inspection using Responsive Design Mode
HOA-ACC-RESP-DASH-002 | Dashboard Tablet | Tablet Layout 768px-1024px | Test responsive layout | High | Dashboard.js | Testing Complete | 2024-11-13 11:18 | Manual Inspection using Responsive Design Mode
HOA-ACC-RESP-DASH-003 | Dashboard Desktop | Desktop Layout > 1024px | Test responsive layout | High | Dashboard.js | Testing Complete | 2024-11-13 11:17 | Manual Inspection using Responsive Design Mode
HOA-ACC-ACC-DASH-001 | Dashboard Access | Section Navigation | Test section accessibility | High | Dashboard.js | Testing Complete | 2024-11-13 11:20 | Manual Inspection using Responsive Design Mode
New Account Modal (NewAccountModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ACC-UT-NEW-001 | Property Select | Property Selection | Test property lookup | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Testing. Was able to select from the property dropdown menu which prevents errors in user input.
HOA-ACC-UT-NEW-002 | Date Input | Date Validation | Test effective date handling | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Testing. Date is validated and must be a valid pick from the calendar
HOA-ACC-UT-NEW-003 | Account Setup | Setup Process | Test account initialization | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Testing. Confirmed the new account creation in database. Tested the user login info afterwards
HOA-ACC-IT-NEW-001 | Create Process | Complete Flow | Test account creation flow | High | NewAccountModal.js, apiService.js | Testing Complete | 2024-11-27 14:21 | Manual Testing. Test the complete flow from selection to creation and registration. No Issues
HOA-ACC-RESP-NEW-001 | Create Mobile | Mobile Modal < 768px | Test form layout | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Inspection using Responsive Design Mode
HOA-ACC-RESP-NEW-002 | Create Tablet | Tablet Modal 768px-1024px | Test form layout | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Inspection using Responsive Design Mode
HOA-ACC-RESP-NEW-003 | Create Desktop | Desktop Layout > 1024px | Test form layout | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Inspection using Responsive Design Mode
HOA-ACC-ACC-NEW-001 | Create Access | Form Navigation | Test form accessibility | High | NewAccountModal.js | Testing Complete | 2024-11-27 14:21 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available

## Announcement
Announcements Page (AnnouncementsNews.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ANT-UT-PAGE-001 | Carousel | Event Display | Test carousel rendering | High | AnnouncementsNews.js | Testing Complete | 2024-11-13 11:20 | Manual Inspection, Rendered with Picture, Classification, Title, Date, Text
HOA-ANT-UT-PAGE-002 | Calendar View | Event Display | Test calendar rendering | High | AnnouncementsNews.js | Testing Complete | 2024-11-13 11:23 | Manual Inspection, Rendered Current Date, Events, Events are selectable
HOA-ANT-IT-PAGE-001 | Data Loading | Initial Load | Test announcement fetching | High | AnnouncementsNews.js, apiService.js | Testing Complete | 2024-11-13 11:28 | Manual Inspection,Current Announcements and Events displayed.
HOA-ANT-RESP-PAGE-001 | Page Mobile | Mobile Layout < 768px | Test responsive layout | High | AnnouncementsNews.js | Testing Complete | 2024-11-13 11:30 | Manual Inspection using Responsive Design Mode
HOA-ANT-RESP-PAGE-002 | Page Tablet | Tablet Layout 768px-1024px | Test responsive layout | High | AnnouncementsNews.js | Testing Complete | 2024-11-13 11:30 | Manual Inspection using Responsive Design Mode
HOA-ANT-RESP-PAGE-003 | Page Desktop | Desktop Layout > 1024px | Test responsive layout | High | AnnouncementsNews.js | Testing Complete | 2024-11-13 11:30 | Manual Inspection using Responsive Design Mode
HOA-ANT-ACC-PAGE-001 | Page Access | Content Navigation | Test page accessibility | High | AnnouncementsNews.js | Testing Complete | 2024-11-13 11:31 | Manual Inspection using Responsive Design Mode
Create Announcement Modal (CreateAnnouncementModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ANT-UT-CRT-001 | Type Selection | Event/Announcement | Test type selection | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-13 11:38 | Manual testing, types are correctly selected and displayed
HOA-ANT-UT-CRT-002 | Date Selection | Date Validation | Test date handling | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-13 11:39 | Manual testing, Date form will not allow any date that doesn't exist
HOA-ANT-UT-CRT-003 | Media Upload | File Upload | Test image upload | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-13 11:42 | Manual testing of pictures uploaded with message. 2 Recent test for future events
HOA-ANT-IT-CRT-001 | Create Process | Complete Flow | Test creation process | High | CreateAnnouncementModal.js, apiService.js | Testing Complete | 2024-11-13 11:42 | Manual testing, the announcement was successfully created and immediately displayed
HOA-ANT-RESP-CRT-001 | Create Mobile | Mobile Modal < 768px | Test form layout | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-14 12:17 | Manual Inspection using Responsive Design Mode. Issue resolved.
HOA-ANT-RESP-CRT-002 | Create Tablet | Tablet Modal 768px-1024px | Test form layout | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-13 11:42 | Manual Inspection using Responsive Design Mode
HOA-ANT-RESP-CRT-003 | Create Desktop | Desktop Modal > 1024px | Test form layout | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-13 11:42 | Manual Inspection using Responsive Design Mode
HOA-ANT-ACC-CRT-001 | Create Access | Form Navigation | Test form accessibility | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-13 11:42 | Manual Inspection using Responsive Design Mode
Announcement Components
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ANT-UT-CAR-001 | Carousel Card | Content Display | Test card content | High | AnnouncementCard.js | Testing Complete | 2024-11-13 11:50 | Manual Inspection, all content displayed
HOA-ANT-UT-CAR-002 | Carousel | Carousel Navigation | Test carousel controls | High | AnnouncementsCarousel.js | Testing Complete | 2024-11-13 11:50 | Manual Inspection, carousel responds to controls in every view
HOA-ANT-UT-CAL-001 | Calendar | Event Display | Test event rendering | High | AnnouncementCalendar.js | Testing Complete | 2024-11-13 11:50 | Manual Inspection, Previous and newly created events rendered in month and agenda views
HOA-ANT-RESP-CAR-001 | Card Mobile | Mobile Card < 768px | Test card layout | High | AnnouncementCard.js | Testing Complete | 2024-11-14 12:17 | Manual Inspection using Responsive Design Mode. Issue Resolved
HOA-ANT-RESP-CAR-002 | Card Tablet | Tablet Card 768px-1024px | Test card layout | High | AnnouncementCard.js | Testing Complete | 2024-11-14 14:25 | Manual Inspection using Responsive Design Mode. Issue Resolved
HOA-ANT-RESP-CAR-003 | Card Desktop | Desktop Card > 1024px | Test card layout | High | AnnouncementCard.js | Testing Complete | 2024-11-13 11:50 | Manual Inspection using Responsive Design Mode
HOA-ANT-ACC-CAR-001 | Card Access | Card Navigation | Test card accessibility | High | AnnouncementCard.js | Testing Complete | 2024-11-13 11:50 | Manual Inspection using Responsive Design Mode

## Authentication
Login Component (Login.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-AUTH-UT-LOG-001 | Login Form | Email Validation | Test email format validation | High | Login.js, AuthContext.js | Testing Complete | 2024-11-13 11:00 | Manual Inspection but should be done with automated
HOA-AUTH-UT-LOG-002 | Login Form | Password Validation | Test password requirements | High | Login.js, AuthContext.js | Testing Complete | 2024-11-13 11:00 | Manual Inspection but should be done with automated
HOA-AUTH-IT-LOG-001 | Login Process | Authentication Flow | Test complete login process with token | High | Login.js, AuthContext.js, apiService.js | Testing Complete | 2024-11-13 11:00 | Manual Inspection but should be done with automated
HOA-AUTH-SEC-LOG-001 | Login Security | Token Management | Test token storage and validation | High | Login.js, AuthContext.js, axiosConfig.js | Testing Complete | 2024-11-13 10:38 | Server Log, Manual Inspection of Local Storage
HOA-AUTH-RESP-LOG-001 | Login Mobile | Mobile Layout < 768px | Test form layout and inputs | High | Login.js | Testing Complete | 2024-11-13 10:35 | Manual Inspection using Responsive Design Mode
HOA-AUTH-RESP-LOG-002 | Login Tablet | Tablet Layout 768px-1024px | Test form layout and inputs | High | Login.js | Testing Complete | 2024-11-13 10:35 | Manual Inspection using Responsive Design Mode
HOA-AUTH-RESP-LOG-003 | Login Desktop | Desktop Layout > 1024px | Test form layout and inputs | High | Login.js | Testing Complete | 2024-11-13 10:33 | Manual Inspection using Responsive Design Mode
2.2 Registration Modal (RegistrationModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-AUTH-UT-REG-001 | Registration Form | Code Validation | Test registration code validation | High | RegistrationModal.js, apiService.js | Testing Complete | 2024-11-27 15:21 | Manual Testing. Issue handled. Code validated successfully
HOA-AUTH-UT-REG-002 | Registration Form | Personal Info | Test personal info collection | High | RegistrationModal.js | Testing Complete | 2024-11-27 15:21 | Manual Testing. Issue handled. Information collected and validated
HOA-AUTH-IT-REG-001 | Registration Process | Complete Flow | Test full registration process | High | RegistrationModal.js, apiService.js | Testing Complete | 2024-11-27 15:21 | Manual Testing. Successful. Resolved issue and added success message and navigation
HOA-AUTH-RESP-REG-001 | Registration Mobile | Mobile Modal < 768px | Test modal layout and form | High | RegistrationModal.js | Testing Complete | 2024-11-27 15:21 | Manual Inspection using Responsive Design Mode
HOA-AUTH-RESP-REG-002 | Registration Tablet | Tablet Modal 768px-1024px | Test modal layout and form | High | RegistrationModal.js | Testing Complete | 2024-11-27 15:21 | Manual Inspection using Responsive Design Mode
HOA-AUTH-RESP-REG-003 | Registration Desktop | Desktop Modal > 1024px | Test modal layout and form | High | RegistrationModal.js | Testing Complete | 2024-11-27 15:21 | Manual Inspection using Responsive Design Mode
HOA-AUTH-ACC-REG-001 | Registration Accessibility | Modal Navigation | Test modal keyboard navigation | High | RegistrationModal.js | Testing Complete | 2024-11-27 15:21 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Password Reset Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-AUTH-UT-PASS-001 | Reset Form | Email Validation | Test reset email validation | High | ForgotPasswordModal.js | Testing Complete | 2024-11-13 10:56 | Manual Inspection, Form and email confirmation
HOA-AUTH-IT-PASS-001 | Reset Process | Reset Flow | Test complete reset process | High | ForgotPasswordModal.js, apiService.js | Testing Complete | 2024-11-13 10:56 | Manual Inspection, Email confirm, Temp Login, Password Reset
HOA-AUTH-RESP-PASS-001 | Reset Mobile | Mobile Modal < 768px | Test modal layout and form | High | ForgotPasswordModal.js | Testing Complete | 2024-11-13 10:56 | Manual Inspection using Responsive Design Mode
HOA-AUTH-RESP-PASS-002 | Reset Tablet | Tablet Modal 768px-1024px | Test modal layout and form | High | ForgotPasswordModal.js | Testing Complete | 2024-11-13 10:56 | Manual Inspection using Responsive Design Mode
HOA-AUTH-RESP-PASS-003 | Reset Desktop | Desktop Modal > 1024px | Test modal layout and form | High | ForgotPasswordModal.js | Testing Complete | 2024-11-13 10:56 | Manual Inspection using Responsive Design Mode
HOA-AUTH-ACC-PASS-001 | Reset Accessibility | Form Navigation | Test form accessibility | High | ForgotPasswordModal.js | Testing Complete | 2024-11-13 10:56 | Manual Inspection using Responsive Design Mode

## Board Management
Board Dashboard (BoardMemberDashboard.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-BRD-UT-BDASH-001 | Dashboard Cards | Permission Display | Test permission-based card display | High | BoardMemberDashboard.js, AuthContext.js | Testing Complete | 2024-11-14 12:38 | Manual Testing. Logged in and viewed dashboard with each type of role
HOA-BRD-UT-BDASH-002 | Action Buttons | Button State | Test button enable/disable logic | High | BoardMemberDashboard.js | Testing Complete | 2024-11-14 12:38 | Manual Testing. Logged in and viewed dashboard with each type of role
HOA-BRD-IT-BDASH-001 | Dashboard Actions | Action Triggers | Test all action button triggers | High | BoardMemberDashboard.js, apiService.js | Testing Complete | 2024-11-14 12:40 | Manual Testing. Each button triggers the correct modal.
HOA-BRD-RESP-BDASH-001 | Dashboard Mobile | Mobile Layout < 768px | Test card grid layout | High | BoardMemberDashboard.js | Testing Complete | 2024-11-14 12:42 | Manual Inspection using Responsive Design Mode
HOA-BRD-RESP-BDASH-002 | Dashboard Tablet | Tablet Layout 768px-1024px | Test card grid layout | High | BoardMemberDashboard.js | Testing Complete | 2024-11-14 12:42 | Manual Inspection using Responsive Design Mode
HOA-BRD-RESP-BDASH-003 | Dashboard Desktop | Desktop Layout > 1024px | Test card grid layout | High | BoardMemberDashboard.js | Testing Complete | 2024-11-14 12:42 | Manual Inspection using Responsive Design Mode
HOA-BRD-ACC-BDASH-001 | Dashboard Accessibility | Card Navigation | Test card keyboard navigation | High | BoardMemberDashboard.js | Testing Complete | 2024-11-14 12:45 | Manual Inspection. Able to tab through and select cards using enter
Board Member Settings Modal (BoardMemberSettingsModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-BRD-UT-BSET-001 | Role Form | Role Creation | Test role creation form | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-14 12:47 | Manual Testing. Role Created and visible in both UI and database
HOA-BRD-UT-BSET-002 | Permissions | Permission Toggle | Test permission toggles | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-14 12:47 | Manual Testing. New role permissions changes, visible in both UI and database
HOA-BRD-IT-BSET-001 | Role Management | Complete Flow | Test role creation flow | High | BoardMemberSettingsModal.js, apiService.js | Testing Complete | 2024-11-14 12:47 | Manual Testing. Role created and ability to be assigned, modified confirmed
HOA-BRD-RESP-BSET-001 | Settings Mobile | Mobile Modal < 768px | Test modal layout | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-14 12:50 | Manual Inspection using Responsive Design Mode
HOA-BRD-RESP-BSET-002 | Settings Tablet | Tablet Modal 768px-1024px | Test modal layout | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-14 12:50 | Manual Inspection using Responsive Design Mode
HOA-BRD-RESP-BSET-003 | Settings Desktop | Desktop Modal > 1024px | Test modal layout | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-14 12:50 | Manual Inspection using Responsive Design Mode
HOA-BRD-ACC-BSET-001 | Settings Accessibility | Form Navigation | Test form accessibility | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-14 12:55 | Manual Inspection. Able to select options and change fields within modal with keyboard
Update Board Members Modal (UpdateBoardMembersModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-BRD-UT-UPD-001 | Member Search | Search Function | Test member search | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-14 13:34 | Manual Inspection.
HOA-BRD-UT-UPD-002 | Role Assignment | Role Selection | Test role assignment | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-14 13:34 | Manual Inspection.
HOA-BRD-IT-UPD-001 | Member Update | Complete Flow | Test member update flow | High | UpdateBoardMembersModal.js, apiService.js | Testing Complete | 2024-11-14 13:34 | Manual Inspection. Issues resolved. Cases of multiple assigns on same day or duplicate lifetime roles
HOA-BRD-RESP-UPD-001 | Update Mobile | Mobile Modal < 768px | Test modal layout | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-14 17:07 | Manual Inspection using Responsive Design Mode
HOA-BRD-RESP-UPD-002 | Update Tablet | Tablet Modal 768px-1024px | Test modal layout | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-14 12:58 | Manual Inspection using Responsive Design Mode
HOA-BRD-RESP-UPD-003 | Update Desktop | Desktop Modal > 1024px | Test modal layout | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-14 12:58 | Manual Inspection using Responsive Design Mode
HOA-BRD-ACC-UPD-001 | Update Accessibility | Modal Navigation | Test modal accessibility | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-14 13:36 | Manual Inspection. Able to select options and change fields within modal with keyboard

## Document
Documents Page (Documents.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-DOC-UT-PAGE-001 | View Toggle | Grid/List Toggle | Test view switching | High | Documents.js | Testing Complete | 2024-11-14 20:43 | Manual Testing for the toggle
HOA-DOC-UT-PAGE-002 | Document List | Document Display | Test document listing | High | Documents.js | Testing Complete | 2024-11-14 20:45 | Manual Testing. Examination that all document listings are present from the database.
HOA-DOC-UT-PAGE-003 | Sort Function | Sort Operation | Test sort functionality | High | Documents.js | Testing Complete | 2024-11-14 20:50 | Manual Testing. Sort by Title and by date. Corrected Issue
HOA-DOC-IT-PAGE-001 | Document Load | Initial Load | Test document fetching | High | Documents.js, apiService.js | Testing Complete | 2024-11-14 20:51 | Manual Testing and visual inspection. Document page loads documents as expected. Give loading indication while waiting
HOA-DOC-RESP-PAGE-001 | Document Mobile | Mobile Layout < 768px | Test document grid/list | High | Documents.js | Testing Complete | 2024-11-14 20:55 | Manual Inspection using Responsive Design Mode
HOA-DOC-RESP-PAGE-002 | Document Tablet | Tablet Layout 768px-1024px | Test document grid/list | High | Documents.js | Testing Complete | 2024-11-14 20:55 | Manual Inspection using Responsive Design Mode
HOA-DOC-RESP-PAGE-003 | Document Desktop | Desktop Layout > 1024px | Test document grid/list | High | Documents.js | Testing Complete | 2024-11-14 20:55 | Manual Inspection using Responsive Design Mode
Upload Document Modal (UploadDocumentModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-DOC-UT-UPL-001 | File Input | File Selection | Test file selection | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:07 | Manual Testing. Allows the selection of a file through Windows explorer window
HOA-DOC-UT-UPL-002 | File Validation | File Type Check | Test file type validation | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:08 | Manual Testing. The popup window will only display supported file types for selection
HOA-DOC-UT-UPL-003 | Metadata Form | Form Validation | Test metadata collection | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:12 | Manual Testing. Form is validated before submission. Missing fields are highlighted for the user upon failed attempt at upload.
HOA-DOC-IT-UPL-001 | Upload Process | Complete Flow | Test upload process | High | UploadDocumentModal.js, apiService.js | Testing Complete | 2024-11-14 21:12 | Manual Testing. Document uploaded through modal. Able to retrieve/download back out.
HOA-DOC-RESP-UPL-001 | Upload Mobile | Mobile Modal < 768px | Test modal layout | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:16 | Manual Inspection using Responsive Design Mode
HOA-DOC-RESP-UPL-002 | Upload Tablet | Tablet Modal 768px-1024px | Test modal layout | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:16 | Manual Inspection using Responsive Design Mode
HOA-DOC-RESP-UPL-003 | Upload Desktop | Desktop Modal > 1024px | Test modal layout | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:16 | Manual Inspection using Responsive Design Mode
HOA-DOC-ACC-UPL-001 | Upload Access | Form Navigation | Test form accessibility | High | UploadDocumentModal.js | Testing Complete | 2024-11-14 21:16 | Manual Inspection using Responsive Design Mode
Document Card Component (DocumentCard.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-DOC-UT-CARD-001 | Info Display | Document Info | Test info display | High | DocumentCard.js | Testing Complete | 2024-11-14 21:50 | Manual Inspection. All info displayed as required
HOA-DOC-UT-CARD-002 | Actions | Download File | Test document download button | High | DocumentCard.js | Testing Complete | 2024-11-14 21:51 | Manual Inspection. Was able to successfully download 3 out of 3 documents.
HOA-DOC-RESP-CARD-001 | Card Mobile | Mobile Layout < 768px | Test card layout | High | DocumentCard.js | Testing Complete | 2024-11-14 21:52 | Manual Inspection using Responsive Design Mode
HOA-DOC-RESP-CARD-002 | Card Tablet | Tablet Layout 768px-1024px | Test card layout | High | DocumentCard.js | Testing Complete | 2024-11-14 21:52 | Manual Inspection using Responsive Design Mode
HOA-DOC-RESP-CARD-003 | Card Desktop | Desktop Layout > 1024px | Test card layout | High | DocumentCard.js | Testing Complete | 2024-11-14 21:52 | Manual Inspection using Responsive Design Mode
HOA-DOC-ACC-CARD-001 | Card Access | Button Access | Test button accessibility | High | DocumentCard.js | Testing Complete | 2024-11-14 21:52 | Manual Inspection. Buttons were accessible by keyboard.

## Message
Messages Page (Messages.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-MSG-UT-PAGE-001 | View Toggle | Timeline/Thread Toggle | Test view switching | High | Messages.js | Testing Complete | 2024-11-14 12:21 | Manual Testing for the toggle functionality. View change confirmed
HOA-MSG-UT-PAGE-002 | Message List | Message Display | Test message listing | High | Messages.js | Testing Complete | 2024-11-14 12:21 | Manual Testing. Messages displayed in the Message List component. Loading screen in place while waiting
HOA-MSG-IT-PAGE-001 | Message Load | Initial Load | Test message fetching | High | Messages.js, apiService.js | Testing Complete | 2024-11-14 12:21 | Manual Testing. Messages loaded into list upon Message page selection. Loading screen in place while waiting
HOA-MSG-RESP-PAGE-001 | Message Mobile | Mobile Layout < 768px | Test message list | High | Messages.js | Testing Complete | 2024-11-14 12:34 | Manual Inspection using Responsive Design Mode
HOA-MSG-RESP-PAGE-002 | Message Tablet | Tablet Layout 768px-1024px | Test split view | High | Messages.js | Testing Complete | 2024-11-14 12:34 | Manual Inspection using Responsive Design Mode
HOA-MSG-RESP-PAGE-003 | Message Desktop | Dektop Layout > 1024px | Test split view | High | Messages.js | Testing Complete | 2024-11-14 12:34 | Manual Inspection using Responsive Design Mode
HOA-MSG-ACC-PAGE-001 | Message Access | List Navigation | Test list accessibility | High | Messages.js | Testing Complete | 2024-11-14 12:34 | Manual Inspection using Responsive Design Mode
New Message Modal (NewMessageModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-MSG-UT-NEW-001 | Recipient Select | Search Function | Test recipient search | High | NewMessageModal.js | Testing Complete | 2024-11-14 12:55 | Manual Testing.. Search functionality renders up to 6 results
HOA-MSG-UT-NEW-002 | Message Form | Message Input | Test message composition | High | NewMessageModal.js | Testing Complete | 2024-11-14 12:55 | Manual Testing.. Message input recieves user input and transfer to review
HOA-MSG-IT-NEW-001 | Send Process | Complete Flow | Test message sending | High | NewMessageModal.js, apiService.js | Testing Complete | 2024-11-14 12:57 | Manual Testing. Flow tested numerous times through message detail tree testing
HOA-MSG-RESP-NEW-001 | Compose Mobile | Mobile Modal < 768px | Test modal layout | High | NewMessageModal.js | Testing Complete | 2024-11-14 13:00 | Manual Inspection using Responsive Design Mode
HOA-MSG-RESP-NEW-002 | Compose Tablet | Tablet Modal 768px-1024px | Test modal layout | High | NewMessageModal.js | Testing Complete | 2024-11-14 13:00 | Manual Inspection using Responsive Design Mode
HOA-MSG-RESP-NEW-003 | Compose Desktop | Desktop Modal > 1024px | Test modal layout | High | NewMessageModal.js | Testing Complete | 2024-11-14 13:00 | Manual Inspection using Responsive Design Mode
HOA-MSG-ACC-NEW-001 | Compose Access | Form Navigation | Test form accessibility | High | NewMessageModal.js | Testing Complete | 2024-11-14 13:00 | Manual Inspection using Responsive Design Mode
Message Detail Component (MessageDetail.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-MSG-UT-DTL-001 | Content Display | Message Content | Test content display | High | MessageDetail.js | Testing Complete | 2024-11-14 10:00 | Manual Testing., displays content of single message
HOA-MSG-UT-DTL-002 | Thread View | Thread Display | Test thread organization | High | MessageDetail.js | Testing Complete | 2024-11-14 10:00 | Manual Testing., displays threaded content in order and by level. Issue resolved
HOA-MSG-IT-DTL-001 | Reply Function | Reply Process | Test reply functionality | High | MessageDetail.js, apiService.js | Testing Complete | 2024-11-14 10:00 | Manual Testing.. Triggers Reply modal and replies to the correct parent message. Issue resolved. Correct parent id wasn't set for each of the threaded messages.
HOA-MSG-RESP-DTL-001 | Detail Mobile | Mobile Layout < 768px | Test detail view | High | MessageDetail.js | Testing Complete | 2024-11-14 10:00 | Manual Inspection using Responsive Design Mode
HOA-MSG-RESP-DTL-002 | Detail Tablet | Tablet Layout 768px-1024px | Test detail view | High | MessageDetail.js | Testing Complete | 2024-11-14 10:00 | Manual Inspection using Responsive Design Mode
HOA-MSG-RESP-DTL-003 | Detail Desktop | Dektop Layout > 1024px | Test detail view | High | MessageDetail.js | Testing Complete | 2024-11-14 10:00 | Manual Inspection using Responsive Design Mode
HOA-MSG-ACC-DTL-001 | Detail Access | Content Navigation | Test view accessibility | High | MessageDetail.js | Testing Complete | 2024-11-14 10:00 | Manual Inspection using Responsive Design Mode

## Payment
Payments Page (Payments.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-PAY-UT-PAGE-001 | Balance Display | Balance Info | Test balance information | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Testing. Balance info present and verified
HOA-PAY-UT-PAGE-002 | Transaction List | List Display | Test transaction listing | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Testing. Transactions listed in order.
HOA-PAY-UT-PAGE-003 | Payment Actions | Action Buttons | Test payment actions | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Testing. Buttons trigger modals properly
HOA-PAY-IT-PAGE-001 | Payment Load | Data Loading | Test payment history load | High | Payments.js, apiService.js | Testing Complete | 2024-11-14 14:04 | Manual Testing. All data loaded on page load. Loading screen in place while waiting
HOA-PAY-RESP-PAGE-001 | Payment Mobile | Mobile Layout < 768px | Test responsive layout | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-PAGE-002 | Payment Tablet | Tablet Layout 768px-1024px | Test responsive layout | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-PAGE-003 | Payment Desktop | Desktop Layout > 1024px | Test responsive layout | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Inspection using Responsive Design Mode
HOA-PAY-ACC-PAGE-001 | Payment Access | Page Navigation | Test page accessibility | High | Payments.js | Testing Complete | 2024-11-14 14:04 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Payment Modal (PaymentModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-PAY-UT-PAY-001 | Amount Input | Validation | Test amount validation | High | PaymentModal.js | Testing Complete | 2024-11-14 15:00 | Manual Testing.. Validates number, non negative, non exponential
HOA-PAY-UT-PAY-002 | Card Selection | Card Display | Test card selection | High | PaymentModal.js | Testing Complete | 2024-11-14 15:00 | Manual Testing.. Cards are displayed and able to be selected. Unselected cards standout from selected card
HOA-PAY-IT-PAY-001 | Payment Process | Complete Flow | Test payment submission | High | PaymentModal.js, apiService.js | Testing Complete | 2024-11-14 15:00 | Manual Testing.. Payment is able to be made, balance is updated and transaction is updated
HOA-PAY-RESP-PAY-001 | Payment Mobile | Mobile Modal < 768px | Test form layout | High | PaymentModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-PAY-002 | Payment Tablet | Tablet Modal 768px-1024px | Test form layout | High | PaymentModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-PAY-003 | Payment Desktop | Desktop Modal > 1024px | Test form layout | High | PaymentModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode
HOA-PAY-ACC-PAY-001 | Payment Accessibility | Form Navigation | Test form accessibility | High | PaymentModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Card Management Modal (CardManagementModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-PAY-UT-CARD-001 | Card List | List Display | Test card listing | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:10 | Manual Testing.. Lists all active cards
HOA-PAY-UT-CARD-002 | Add Card | Card Addition | Test new card addition | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:12 | Manual Testing.. Add card button triggers form. Card info validated to 16 numbers
HOA-PAY-UT-CARD-003 | Card Default | Default Setting | Test default card setting | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:12 | Manual Testing.. Able to change between default cards
HOA-PAY-IT-CARD-001 | Card Process | Complete Flow | Test card management flow | High | CardManagementModal.js, apiService.js | Testing Complete | 2024-11-14 15:15 | Manual Testing.. Card created, rendered, available for use. Database updated.
HOA-PAY-RESP-CARD-001 | Card Mobile | Mobile Modal < 768px | Test modal layout | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-CARD-002 | Card Tablet | Tablet Modal 768px-1024px | Test modal layout | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-CARD-003 | Card Desktop | Desktop Modal > 1024px | Test modal layout | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode
HOA-PAY-ACC-CARD-001 | Card Access | Modal Navigation | Test modal accessibility | High | CardManagementModal.js | Testing Complete | 2024-11-14 15:03 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Payment History Modal (PaymentHistoryModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-PAY-UT-HIST-001 | Detail Display | Payment Details | Test detail display | High | PaymentHistoryModal.js | Testing Complete | 2024-11-14 15:15 | Manual Inspection. All transactions displayed by year, revers chronological order. Balances are correct
HOA-PAY-UT-HIST-002 | Receipt View | Receipt Display | Test receipt generation | High | PaymentHistoryModal.js | Testing Complete | 2024-11-14 15:15 | Manual Inspection, display online receipt on request
HOA-PAY-IT-HIST-001 | History Load | Data Loading | Test history fetching | High | PaymentHistoryModal.js, apiService.js | Testing Complete | 2024-11-14 15:15 | Manual Inspection, all data loaded and updates rendered on payment submission
HOA-PAY-RESP-HIST-001 | History Mobile | Mobile Modal < 768px | Test modal layout | High | PaymentHistoryModal.js | Testing Complete | 2024-11-14 15:20 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-HIST-002 | History Tablet | Tablet Modal 768px-1024px | Test modal layout | High | PaymentHistoryModal.js | Testing Complete | 2024-11-14 15:20 | Manual Inspection using Responsive Design Mode
HOA-PAY-RESP-HIST-003 | History Desktop | Desktop Modal > 1024px | Test modal layout | High | PaymentHistoryModal.js | Testing Complete | 2024-11-14 15:20 | Manual Inspection using Responsive Design Mode
HOA-PAY-ACC-HIST-001 | History Access | Modal Navigation | Test modal accessibility | High | PaymentHistoryModal.js | Testing Complete | 2024-11-14 15:20 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available

## Survey
Survey Page (Survey.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SUR-UT-PAGE-001 | Survey List | List Display | Test survey listing | High | Survey.js | Testing Complete | 2024-11-14 13:04 | Manual Testing.. Survey cards rendered on load
HOA-SUR-UT-PAGE-002 | Filter Toggle | Active/Inactive | Test filter functionality | High | Survey.js | Testing Complete | 2024-11-14 13:04 | Manual Testing.. Toggles correctly switches views of active/inactive surveys
HOA-SUR-IT-PAGE-001 | Survey Load | Initial Load | Test survey fetching | High | Survey.js, apiService.js | Testing Complete | 2024-11-14 13:04 | Manual Testing.. All surveys loaded upon page load. Loading graphic in place while waiting for load
HOA-SUR-RESP-PAGE-001 | Survey Mobile | Mobile Layout < 768px | Test list layout | High | Survey.js | Testing Complete | 2024-11-14 13:08 | Manual Inspection using Responsive Design Mode
HOA-SUR-RESP-PAGE-002 | Survey Tablet | Tablet Layout 768px-1024px | Test list layout | High | Survey.js | Testing Complete | 2024-11-14 13:08 | Manual Inspection using Responsive Design Mode
HOA-SUR-RESP-PAGE-003 | Survey Desktop | Desktop Layout > 1024px | Test list layout | High | Survey.js | Testing Complete | 2024-11-14 13:08 | Manual Inspection using Responsive Design Mode
HOA-SUR-ACC-PAGE-001 | Survey Access | List Navigation | Test list accessibility | High | Survey.js | Testing Complete | 2024-11-14 13:10 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Create Survey Modal (CreateSurveyModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SUR-UT-CRT-001 | Question Input | Question Form | Test question creation | High | CreateSurveyModal.js | Testing Complete | 2024-11-14 13:10 | Manual Testing. Form took in user input and succesfully created and rendered the new survey
HOA-SUR-UT-CRT-002 | Answer Options | Option Management | Test option handling | High | CreateSurveyModal.js | Testing Complete | 2024-11-14 13:10 | Manual Testing. Form took in user input and succesfully created and rendered the new survey
HOA-SUR-IT-CRT-001 | Create Process | Complete Flow | Test creation process | High | CreateSurveyModal.js, apiService.js | Testing Complete | 2024-11-14 13:10 | Manual Testing. Form took in user input and succesfully created and rendered the new survey
HOA-SUR-RESP-CRT-001 | Create Mobile | Mobile Modal < 768px | Test form layout | High | CreateSurveyModal.js | Testing Complete | 2024-11-14 13:16 | Manual Inspection using Responsive Design Mode. Issue resolved. Top covered by header
HOA-SUR-RESP-CRT-002 | Create Tablet | Tablet Modal 768px-1024px | Test form layout | High | CreateSurveyModal.js | Testing Complete | 2024-11-14 13:16 | Manual Inspection using Responsive Design Mode
HOA-SUR-RESP-CRT-003 | Create Desktop | Desktop Modal > 1024px | Test form layout | High | CreateSurveyModal.js | Testing Complete | 2024-11-14 13:16 | Manual Inspection using Responsive Design Mode
HOA-SUR-ACC-CRT-001 | Create Access | Form Navigation | Test form accessibility | High | CreateSurveyModal.js | Testing Complete | 2024-11-14 13:16 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Survey Results Modal (SurveyResultsModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SUR-UT-RES-001 | Results Display | Data Visualization | Test results display | High | SurveyResultsModal.js | Testing Complete | 2024-11-14 13:18 | Manual Testing. Results displayed as bar graph and text. Graph is interactive
HOA-SUR-IT-RES-001 | Results Load | Data Loading | Test results fetching | High | SurveyResultsModal.js, apiService.js | Testing Complete | 2024-11-14 13:18 | Manual Testing. Results displayed as bar graph and text. Graph is interactive. Data loaded in order to display
HOA-SUR-RESP-RES-001 | Results Mobile | Mobile Modal < 768px | Test results layout | High | SurveyResultsModal.js | Testing Complete | 2024-11-14 13:26 | Manual Inspection using Responsive Design Mode. Issue resolved. Top covered by header
HOA-SUR-RESP-RES-002 | Results Tablet | Tablet Modal 768px-1024px | Test results layout | High | SurveyResultsModal.js | Testing Complete | 2024-11-14 13:26 | Manual Inspection using Responsive Design Mode
HOA-SUR-RESP-RES-003 | Results Desktop | Desktop Modal > 1024px | Test results layout | High | SurveyResultsModal.js | Testing Complete | 2024-11-14 13:26 | Manual Inspection using Responsive Design Mode
HOA-SUR-ACC-RES-001 | Results Access | Results Navigation | Test results accessibility | High | SurveyResultsModal.js | Testing Complete | 2024-11-14 13:26 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Survey Completion Modal (SurveyCompletionModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SUR-UT-COM-001 | Answer Selection | Option Selection | Test answer selection | High | SurveyCompletionModal.js | Testing Complete | 2024-11-14 13:31 | Manual Testing. All the answers are displayed and can be selected.
HOA-SUR-IT-COM-001 | Submit Process | Response Submit | Test submission process | High | SurveyCompletionModal.js, apiService.js | Testing Complete | 2024-11-14 13:31 | Manual Testing. Selected answer successfully submitted. Answer seen in the results tabulation
HOA-SUR-RESP-COM-001 | Complete Mobile | Mobile Modal < 768px | Test form layout | High | SurveyCompletionModal.js | Testing Complete | 2024-11-14 13:35 | Manual Inspection using Responsive Design Mode
HOA-SUR-RESP-COM-002 | Complete Tablet | Tablet Modal 768px-1024px | Test form layout | High | SurveyCompletionModal.js | Testing Complete | 2024-11-14 13:35 | Manual Inspection using Responsive Design Mode
HOA-SUR-RESP-COM-003 | Complete Desktop | Desktop Modal > 1024px | Test form layout | High | SurveyCompletionModal.js | Testing Complete | 2024-11-14 13:35 | Manual Inspection using Responsive Design Mode
HOA-SUR-ACC-COM-001 | Complete Access | Form Navigation | Test form accessibility | High | SurveyCompletionModal.js | Testing Complete | 2024-11-14 13:35 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available

## User
Owner Information (OwnerInfo.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-USR-UT-OWN-001 | Personal Info | Info Display | Test personal info display | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:07 | Manual Testing. Information Present and displayed
HOA-USR-UT-OWN-002 | Contact Info | Info Display | Test contact info display | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:07 | Manual Testing. Information Present and displayed
HOA-USR-UT-OWN-003 | Preferences | Preference Display | Test preference display | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:07 | Manual Testing. Information Present and displayed
HOA-USR-IT-OWN-001 | Info Update | Update Process | Test info update flow | High | OwnerInfo.js, apiService.js | Testing Complete | 2024-11-14 14:18 | Manual Testing. Information update completed, and rendered.
HOA-USR-RESP-OWN-001 | Owner Mobile | Mobile Layout < 768px | Test responsive layout | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:20 | Manual Inspection using Responsive Design Mode
HOA-USR-RESP-OWN-002 | Owner Tablet | Tablet Layout 768px-1024px | Test responsive layout | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:20 | Manual Inspection using Responsive Design Mode
HOA-USR-RESP-OWN-003 | Owner Desktop | Desktop Layout > 1024px | Test responsive layout | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:20 | Manual Inspection using Responsive Design Mode
HOA-USR-ACC-OWN-001 | Owner Access | Section Navigation | Test section accessibility | High | OwnerInfo.js | Testing Complete | 2024-11-14 14:20 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Profile Information (PersonalInfoModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-USR-UT-PROF-001 | Info Form | Form Display | Test form display | High | PersonalInfoModal.js | Testing Complete | 2024-11-14 14:08 | Manual Testing. User information input, changed and rendered
HOA-USR-UT-PROF-002 | Data Validation | Input Validation | Test input validation | High | PersonalInfoModal.js | Testing Complete | 2024-11-14 14:08 | Manual Testing. Validated to only contain characters, spaces, hyphen
HOA-USR-IT-PROF-001 | Update Process | Complete Flow | Test update process | High | PersonalInfoModal.js, apiService.js | Testing Complete | 2024-11-14 14:08 | Manual Testing. Information update completed, and rendered.
HOA-USR-RESP-PROF-001 | Profile Mobile | Mobile Modal < 768px | Test modal layout | High | PersonalInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode
HOA-USR-RESP-PROF-002 | Profile Tablet | Tablet Modal 768px-1024px | Test form layout | High | PersonalInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode
HOA-USR-RESP-PROF-003 | Profile Desktop | Desktop Modal > 1024px | Test form layout | High | PersonalInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode
HOA-USR-ACC-PROF-001 | Profile Access | Form Navigation | Test form accessibility | High | PersonalInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Contact Information Modal (ContactInfoModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-USR-UT-CONT-001 | Email Input | Email Validation | Test email validation | High | ContactInfoModal.js | Testing Complete | 2024-11-14 14:08 | Manual Testing. Validated for email formatting
HOA-USR-UT-CONT-002 | Phone Input | Phone Validation | Test phone validation | High | ContactInfoModal.js | Testing Complete | 2024-11-14 14:08 | Manual Testing. Validated for only numbers, and precences of 10 numbers
HOA-USR-IT-CONT-001 | Update Process | Contact Update | Test update process | High | ContactInfoModal.js, apiService.js | Testing Complete | 2024-11-14 14:08 | Manual Testing. Validated for only numbers, and precences of 10 numbers
HOA-USR-RESP-CONT-001 | Contact Mobile | Mobile Modal < 768px | Test form layout | High | ContactInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode
HOA-USR-RESP-CONT-002 | Contact Tablet | Tablet Modal 768px-1024px | Test form layout | High | ContactInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode
HOA-USR-RESP-CONT-003 | Contact Desktop | Desktop Modal > 1024px | Test form layout | High | ContactInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode
HOA-USR-ACC-CONT-001 | Contact Access | Form Navigation | Test form accessibility | High | ContactInfoModal.js | Testing Complete | 2024-11-14 14:19 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Notification Preferences Modal (NotificationPreferencesModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-NOT-UT-PREF-001 | Master Checkbox | Email Checkbox | Test master email toggle | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:22 | Manual Testing. Enable Email Comms checkbox, enables/disables bottom selections
HOA-NOT-UT-PREF-002 | Category Checkboxes | Category Settings | Test category toggles | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:22 | Manual Testing. Each category, enables/disables notifications, Database updated
HOA-NOT-UT-PREF-003 | Bulk Actions | Enable/Disable All | Test bulk actions | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:22 | Manual Testing. Enables or disables all checkbox selectionss
HOA-NOT-IT-PREF-001 | Save Process | Preference Save | Test save process | High | NotificationPreferencesModal.js, apiService.js | Testing Complete | 2024-11-14 14:23 | Manual Testing. Each category, enables/disables notifications, Database updated
HOA-NOT-RESP-PREF-001 | Preferences Mobile | Mobile Modal < 768px | Test modal layout | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:26 | Manual Inspection using Responsive Design Mode
HOA-NOT-RESP-PREF-002 | Preferences Tablet | Tablet Modal 768px-1024px | Test modal layout | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:26 | Manual Inspection using Responsive Design Mode
HOA-NOT-RESP-PREF-003 | Preferences Desktop | Desktop Modal > 1024px | Test modal layout | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:26 | Manual Inspection using Responsive Design Mode
HOA-NOT-ACC-PREF-001 | Preferences Access | Toggle Navigation | Test toggle accessibility | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-14 14:26 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available

## Assessments
Issue Assessment Modal (IssueAssessmentModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ASS-UT-ISS-001 | Type Selection | Assessment Type | Test assessment type selection | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:29 | Manual Testing. Validated that each of the assessment types was able to be selected.
HOA-ASS-UT-ISS-002 | Rate Selection | Rate Setting | Test rate selection and validation | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:31 | Manual Testing. Validated that each of the assessment rates was able to be selected.
HOA-ASS-UT-ISS-003 | Owner Selection | Search Function | Test owner search and selection | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:32 | Manual Testing. Confirmed that the search text correctly displays matching owner names
HOA-ASS-UT-ISS-004 | Bulk Selection | Mass Assessment | Test "assess all" functionality | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:33 | Manual Testing. "Assess All Active Owners" Checkbox does select all owners for assessment creation
HOA-ASS-IT-ISS-001 | Assessment Process | Complete Flow | Test full assessment creation flow | High | IssueAssessmentModal.js, apiService.js | Testing Complete | 2024-11-27 13:41 | Manaul Testing. Created a test assessment for an individual. Confirmed balance changes, charge created for an assessment with proper assessment details, types and rates.
HOA-ASS-RESP-ISS-001 | Assessment Mobile | Mobile Modal < 768px | Test form layout | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:45 | Manual Inspection using Responsive Design Mode
HOA-ASS-RESP-ISS-002 | Assessment Tablet | Tablet Modal 768px-1024px | Test form layout | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:45 | Manual Inspection using Responsive Design Mode
HOA-ASS-RESP-ISS-003 | Assessment Desktop | Desktop Modal > 1024px | Test form layout | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:45 | Manual Inspection using Responsive Design Mode
HOA-ASS-ACC-ISS-001 | Assessment Access | Form Navigation | Test form accessibility | High | IssueAssessmentModal.js | Testing Complete | 2024-11-27 13:45 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Manage Assessments Modal (ManageAssessmentsModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-ASS-UT-MNG-001 | Type Management | Type Creation | Test assessment type creation | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 13:46 | Manual Testing. Assessment types added successfully, verified in database
HOA-ASS-UT-MNG-002 | Type Management | Type Validation | Test type input validation | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 13:46 | Manual Testing. Allows for any text input, as long as not blank.
HOA-ASS-UT-MNG-003 | Rate Management | Rate Creation | Test rate creation and validation | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 14:13 | Manaul Testing. Validation Issue Resolved. Adds new rates, validates number
HOA-ASS-UT-MNG-004 | Rate Management | Year Validation | Test yearly assessment settings | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 14:13 | Manaul Testing. Validation Issue Resolved. Adds new rates, validates current year or greater or empty if it is not required for a yearly assessment.
HOA-ASS-IT-MNG-001 | Type Process | Complete Flow | Test type management flow | High | ManageAssessmentsModal.js, apiService.js | Testing Complete | 2024-11-27 14:15 | Manual Testing. Validated in database and ability to choose new types and rates for assessments
HOA-ASS-IT-MNG-002 | Rate Process | Complete Flow | Test rate management flow | High | ManageAssessmentsModal.js, apiService.js | Testing Complete | 2024-11-27 14:15 | Manual Testing. Validated in database and ability to choose new types and rates for assessments
HOA-ASS-RESP-MNG-001 | Manage Mobile | Mobile Modal < 768px | Test modal layout | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 14:20 | Manual Inspection using Responsive Design Mode
HOA-ASS-RESP-MNG-002 | Manage Tablet | Tablet Modal 768px-1024px | Test modal layout | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 14:20 | Manual Inspection using Responsive Design Mode
HOA-ASS-RESP-MNG-003 | Manage Desktop | Desktop Modal > 1024px | Test modal layout | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 14:20 | Manual Inspection using Responsive Design Mode
HOA-ASS-ACC-MNG-001 | Manage Access | Modal Navigation | Test modal accessibility | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-27 14:20 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available

## Violations
Issue Violation Modal (IssueViolationModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-VIO-UT-ISS-001 | Violation Form | Type Selection | Test violation type selection | High | IssueViolationModal.js | Testing Complete | 2024-11-27 15:45 | Manual Testing. Able to select a current HOA violaton
HOA-VIO-UT-ISS-002 | Resident Selection | Search Function | Test resident search | High | IssueViolationModal.js | Testing Complete | 2024-11-27 15:45 | Manual Testing. Able to search for an owner. Might want to adjust for property instead
HOA-VIO-IT-ISS-001 | Violation Process | Complete Flow | Test violation creation flow | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-27 15:45 | Manual Testing. Flow confirmed. Violation charge and balance updated. Database confirmed
HOA-VIO-RESP-ISS-001 | Violation Mobile | Mobile Modal < 768px | Test form layout | High | IssueViolationModal.js | Testing Complete | 2024-11-27 15:45 | Manual Inspection using Responsive Design Mode
HOA-VIO-RESP-ISS-002 | Violation Tablet | Tablet Modal 768px-1024px | Test form layout | High | IssueViolationModal.js | Testing Complete | 2024-11-27 15:45 | Manual Inspection using Responsive Design Mode
HOA-VIO-RESP-ISS-003 | Violation Tablet | Desktop Modal > 1024px | Test form layout | High | IssueViolationModal.js | Testing Complete | 2024-11-27 15:45 | Manual Inspection using Responsive Design Mode
HOA-VIO-ACC-ISS-001 | Violation Accessibility | Form Navigation | Test form accessibility | High | IssueViolationModal.js | Testing Complete | 2024-11-27 15:45 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available
Update Violations Modal (UpdateViolationsModal.js)
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-VIO-UT-UPD-001 | Type Management | Type Creation | Test type creation | High | UpdateViolationsModal.js | Testing Complete | 2024-11-27 15:30 | Manual Testing. Able to create a new type of violation "Overcooked Fish"
HOA-VIO-UT-UPD-002 | Rate Management | Rate Setting | Test rate configuration | High | UpdateViolationsModal.js | Testing Complete | 2024-11-27 15:30 | Manual Testing. Able to create a new rate for violation "Overcooked Fish"
HOA-VIO-IT-UPD-001 | Update Process | Complete Flow | Test type update flow | High | UpdateViolationsModal.js, apiService.js | Testing Complete | 2024-11-27 15:30 | Manual Testing. New violation available for assignment and in database
HOA-VIO-RESP-UPD-001 | Update Mobile | Mobile Modal < 768px | Test modal layout | High | UpdateViolationsModal.js | Testing Complete | 2024-11-27 15:30 | Manual Inspection using Responsive Design Mode
HOA-VIO-RESP-UPD-002 | Update Tablet | Tablet Modal 768px-1024px | Test modal layout | High | UpdateViolationsModal.js | Testing Complete | 2024-11-27 15:30 | Manual Inspection using Responsive Design Mode
HOA-VIO-RESP-UPD-003 | Update Tablet | Desktop Modal > 1024px | Test modal layout | High | UpdateViolationsModal.js | Testing Complete | 2024-11-27 15:30 | Manual Inspection using Responsive Design Mode
HOA-VIO-ACC-UPD-001 | Update Accessibility | Modal Navigation | Test modal accessibility | High | UpdateViolationsModal.js | Testing Complete | 2024-11-27 15:30 | Manual Inspection using Responsive Design Mode. Navigation by keyboard available

## Integration
Authentication Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-AUTH-001 | Login Flow | Complete Login | Test standard login process | High | Login.js, AuthContext.js, apiService.js | Testing Complete | 2024-11-30 21:36 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-002 | Login Flow | Board Login | Test board member login and permission loading | High | Login.js, AuthContext.js, apiService.js | Testing Complete | 2024-11-30 21:38 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-003 | Login Flow | First Time Login | Test temporary password change flow | High | Login.js, ChangePasswordModal.js, apiService.js | Testing Complete | 2024-11-30 21:40 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-004 | Register Flow | New Registration | Test new user registration process | High | RegistrationModal.js, apiService.js | Testing Complete | 2024-11-30 21:46 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-005 | Register Flow | Verification | Test registration code verification | High | RegistrationModal.js, apiService.js | Testing Complete | 2024-11-30 21:49 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-006 | Password Reset | Reset Request | Test password reset request flow | High | ForgotPasswordModal.js, apiService.js | Testing Complete | 2024-11-30 21:49 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-007 | Password Reset | Reset Complete | Test password reset completion | High | ForgotPasswordModal.js, apiService.js | Testing Complete | 2024-11-30 21:50 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-008 | Session Handling | Token Refresh | Test automatic token refresh | High | AuthContext.js, apiService.js | Testing Complete | 2024-11-30 21:52 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-009 | Session Handling | Session Expiry | Test session expiration handling | High | AuthContext.js, apiService.js | Testing Complete | 2024-11-30 21:56 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-AUTH-010 | Logout Flow | Complete Logout | Test logout and cleanup process | High | AuthContext.js, apiService.js | Testing Complete | 2024-11-30 21:58 | Manual Testing using HOA Management System Integration Test Plan
Payment Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-PAY-001 | Payment Process | New Payment | Test new payment with existing card | High | PaymentModal.js, apiService.js | Testing Complete | 2024-11-30 22:00 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-002 | Payment Process | New Card Payment | Test payment with new card addition | High | PaymentModal.js, CardManagementModal.js | Testing Complete | 2024-11-30 22:01 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-003 | Payment Process | Failed Payment | Test payment failure handling | High | PaymentModal.js, apiService.js | Testing Complete | 2024-11-30 22:05 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-004 | Card Management | Add Card | Test new card addition flow | High | CardManagementModal.js, apiService.js | Testing Complete | 2024-11-30 22:07 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-005 | Card Management | Remove Card | Test card removal process | High | CardManagementModal.js, apiService.js | Testing Complete | 2024-11-30 22:08 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-006 | Card Management | Default Card | Test default card setting | High | CardManagementModal.js, apiService.js | Testing Complete | 2024-11-30 22:08 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-007 | Receipt Process | Generation | Test receipt generation process | High | PaymentHistoryModal.js, apiService.js | Testing Complete | 2024-11-30 22:11 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-008 | Receipt Process | Download | Test receipt download functionality | High | PaymentHistoryModal.js, apiService.js | Testing Complete | 2024-11-30 22:12 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-009 | History Update | Real-time Update | Test payment history real-time updates | High | Payments.js, apiService.js | Testing Complete | 2024-11-30 22:13 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PAY-010 | History Update | Filter/Search | Test payment history filtering | High | Payments.js, apiService.js | NOT TESTING |  | NOT A THING THAT WE IMPLEMENTED OR NEED TO IMPLEMENT
Document Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-DOC-001 | Upload Process | Single Upload | Test single document upload | High | UploadDocumentModal.js, apiService.js | Testing Complete | 2024-11-30 22:16
HOA-INT-IT-DOC-002 | Upload Process | Batch Upload | Test multiple document upload | High | UploadDocumentModal.js, apiService.js | NOT TESTING |  | NOT A THING THAT WE IMPLEMENTED OR NEED TO IMPLEMENT. DESCRIPTONS AND TITLES AND CAEGORIES WOULD BE AN ISSUE
HOA-INT-IT-DOC-003 | Upload Process | Large Files | Test large file upload handling | High | UploadDocumentModal.js, apiService.js | Testing Complete | 2024-11-30 22:16 | Manual Testing using HOA Management System Integration Test Plan. Slow but can support up to ~4GB if needed
HOA-INT-IT-DOC-004 | Download Process | Single Download | Test single document download | High | Documents.js, apiService.js | Testing Complete | 2024-11-30 22:16 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-DOC-005 | Download Process | Batch Download | Test multiple document download | High | Documents.js, apiService.js | NOT TESTING |  | NOT A THING THAT WE IMPLEMENTED OR NEED TO IMPLEMENT.
HOA-INT-IT-DOC-006 | Update Process | Metadata Update | Test document metadata update | High | DocumentCard.js, apiService.js | Testing Complete | 2024-11-30 22:16 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-DOC-007 | Update Process | File Replace | Test document file replacement | High | DocumentCard.js, apiService.js | Testing Complete | 2024-11-30 22:16 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-DOC-008 | Delete Process | Single Delete | Test single document deletion | High | DocumentCard.js, apiService.js | Testing Complete | 2024-11-30 22:16 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-DOC-009 | Delete Process | Batch Delete | Test multiple document deletion | High | DocumentCard.js, apiService.js | NOT TESTING |  | NOT A THING THAT WE IMPLEMENTED OR NEED TO IMPLEMENT.
HOA-INT-IT-DOC-010 | Search Process | Document Search | Test document search functionality | High | Documents.js, apiService.js | NOT TESTING |  | NOT A THING THAT WE IMPLEMENTED OR NEED TO IMPLEMENT.
Message Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-MSG-001 | Compose Flow | New Message | Test new message creation | High | NewMessageModal.js, apiService.js | Testing Complete | 2024-11-30 22:19
HOA-INT-IT-MSG-002 | Compose Flow | With Attachment | Test message with attachment | High | NewMessageModal.js, apiService.js | NOT TESTING |  | REMOVED REQUIREMENT EARLY. DO NOT WANT PEOPLE SENDING ATTACHMENTS TO EACH OTHER IN MESSAGES. ISSUE FOR HAVING TO POLICE CERTAIN MATERIALS
HOA-INT-IT-MSG-003 | Reply Flow | Direct Reply | Test direct message reply | High | ReplyMessageModal.js, apiService.js | Testing Complete | 2024-11-30 22:20 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-MSG-004 | Reply Flow | Thread Reply | Test threaded message reply | High | ReplyMessageModal.js, apiService.js | Testing Complete | 2024-11-30 22:22 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-MSG-005 | View Flow | Message List | Test message list loading | High | Messages.js, apiService.js | Testing Complete | 2024-11-30 22:22 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-MSG-006 | View Flow | Thread View | Test conversation thread view | High | MessageDetail.js, apiService.js | Testing Complete | 2024-11-30 22:22 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-MSG-007 | Search Flow | User Search | Test message recipient search | High | NewMessageModal.js, apiService.js | Testing Complete | 2024-11-30 22:22 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-MSG-008 | Search Flow | Message Search | Test message content search | High | Messages.js, apiService.js | NOT TESTING |  | NOT A REQUIREMENT
HOA-INT-IT-MSG-009 | Delete Flow | Single Delete | Test single message deletion | High | MessageDetail.js, apiService.js | NOT TESTING |  | I DID NOT IMPLEMENTING DELETION. NOT A REQUIREMENT
HOA-INT-IT-MSG-010 | Delete Flow | Thread Delete | Test conversation thread deletion | High | MessageDetail.js, apiService.js | NOT TESTING |  | I DID NOT IMPLEMENTING DELETION. NOT A REQUIREMENT
Board Member Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-BRD-001 | Role Management | Add Role | Test board role creation | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-002 | Role Management | Update Role | Test role permission update | High | BoardMemberSettingsModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-003 | Member Management | Add Member | Test new board member addition | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-004 | Member Management | Remove Member | Test board member removal | High | UpdateBoardMembersModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-005 | Violation Flow | Issue Violation | Test violation issuance process | High | IssueViolationModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-006 | Violation Flow | Update Types | Test violation type management | High | UpdateViolationsModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-007 | Assessment Flow | Issue Assessment | Test assessment issuance | High | IssueAssessmentModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-008 | Assessment Flow | Manage Rates | Test assessment rate management | High | ManageAssessmentsModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-009 | Account Flow | Create Account | Test new account creation | High | NewAccountModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-BRD-010 | Account Flow | Account Setup | Test account setup completion | High | NewAccountModal.js | Testing Complete | 2024-11-30 22:23 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
Announcement Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-ANC-001 | Create Flow | New Announcement | Test announcement creation | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-002 | Create Flow | With Media | Test media attachment | High | CreateAnnouncementModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-003 | Update Flow | Edit Content | Test announcement editing | High | ManageAnnouncementsModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-004 | Update Flow | Update Media | Test media update | High | ManageAnnouncementsModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-005 | Delete Flow | Remove Item | Test announcement deletion | High | ManageAnnouncementsModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-006 | View Flow | List View | Test announcement list | High | AnnouncementsNews.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-007 | View Flow | Detail View | Test announcement details | High | AnnouncementModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-008 | Calendar Flow | Event Display | Test calendar integration | High | AnnouncementCalendar.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-009 | Calendar Flow | Event Updates | Test calendar updates | High | AnnouncementCalendar.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ANC-010 | Search Flow | Content Search | Test announcement search | High | AnnouncementsNews.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
Survey Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-SRV-001 | Create Flow | New Survey | Test survey creation process | High | CreateSurveyModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-002 | Create Flow | Question Types | Test different question formats | High | CreateSurveyModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-003 | Response Flow | Submit Response | Test survey response submission | High | SurveyCompletionModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-004 | Response Flow | Update Response | Test response modification | High | SurveyCompletionModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-005 | Results Flow | View Results | Test results visualization | High | SurveyResultsModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-006 | Results Flow | Export Results | Test results export | High | SurveyResultsModal.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-007 | List Flow | Active Surveys | Test active survey display | High | Survey.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-008 | List Flow | Past Surveys | Test completed survey history | High | Survey.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-009 | Delete Flow | Survey Removal | Test survey deletion process | High | Survey.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-SRV-010 | Access Flow | Permission Check | Test survey access controls | High | Survey.js | Testing Complete | 2024-11-26 | Manual Testing using HOA Management System Integration Test Plan
Profile Management Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-PRF-001 | Personal Info | Update Info | Test personal info updates | High | PersonalInfoModal.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-002 | Contact Info | Update Contact | Test contact info updates | High | ContactInfoModal.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-003 | Preferences | Update Settings | Test notification preferences | High | NotificationPreferencesModal.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-004 | Password Change | Update Password | Test password change process | High | ChangePasswordModal.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-005 | Email Verify | Verify Email | Test email verification | High | OwnerInfo.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-006 | Profile View | Load Profile | Test profile data loading | High | OwnerInfo.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-007 | Settings Sync | Settings Update | Test settings synchronization | High | Settings.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-008 | Theme Toggle | Theme Change | Test theme preference saving | High | Settings.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-009 | Data Export | Profile Export | Test profile data export | High | OwnerInfo.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-PRF-010 | Account Status | Status Update | Test account status changes | High | OwnerInfo.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
Assessment Integration Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-ASS-001 | Type Creation | New Type | Test new assessment type creation | High | ManageAssessmentsModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-002 | Rate Creation | New Rate | Test new assessment rate creation | High | ManageAssessmentsModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-003 | Bulk Issue | Mass Assessment | Test bulk assessment issuance | High | IssueAssessmentModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-004 | Single Issue | Individual Assessment | Test single assessment issuance | High | IssueAssessmentModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-005 | Yearly Settings | Year Configuration | Test yearly assessment setup | High | ManageAssessmentsModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-006 | Assessment Update | Status Update | Test assessment status changes | High | IssueAssessmentModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-007 | Email Notification | Notice Generation | Test assessment notification | High | IssueAssessmentModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-008 | Permission Check | Access Control | Test role-based permissions | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-009 | Error Handling | Error States | Test error handling and display | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-ASS-010 | Data Refresh | Real-time Updates | Test data refresh after changes | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
Violation Integration Flow
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-INT-IT-VIO-001 | Type Creation | New Type | Test new violation type creation with fine amount | High | UpdateViolationsModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-002 | Type Update | Modify Type | Test updating existing violation type and rate | High | UpdateViolationsModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-003 | Issue Flow | Single Violation | Test complete violation issuance to single resident | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-004 | Photo Upload | Media Handling | Test violation photo upload and storage | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-005 | Notice Generation | Email Creation | Test violation notice generation and email | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-006 | Payment Creation | Fine Processing | Test automatic fine creation in payment system | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-007 | Permission Check | Access Control | Test role-based access for violation management | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-008 | Error Handling | Error States | Test error handling and user feedback | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-009 | History Update | Record Creation | Test violation history recording and display | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-010 | Multiple Issues | Batch Processing | Test handling multiple violations for same resident | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-011 | Due Date Handling | Date Validation | Test due date calculation and validation | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-012 | Status Updates | State Changes | Test violation status lifecycle management | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-013 | Data Refresh | Real-time Updates | Test data refresh after violation changes | High | Both Modals, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-014 | Search Integration | Resident Search | Test resident search in violation context | High | IssueViolationModal.js, apiService.js | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan
HOA-INT-IT-VIO-015 | Dashboard Update | UI Reflection | Test violation reflection in dashboards | High | Both Modals, Dashboard Components | Testing Complete | 2024-11-30 22:33 | Tested last week didn't log it. Manual Testing using HOA Management System Integration Test Plan

## Responsiveness
Layout Components
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-RES-LAY-001 | Header Mobile | Mobile Header | Test header < 768px | High | Header.js | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-LAY-002 | Header Tablet | Tablet Header | Test header 768px-1024px | High | Header.js | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-LAY-003 | Sidebar Mobile | Mobile Sidebar | Test sidebar < 768px | High | Sidebar.js | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-LAY-004 | Content Flow | Content Adapt | Test content flow | High | Layout.js | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-LAY-005 | Grid System | Grid Response | Test grid layouts | High | All Components | Testing Complete | 2024-11-27 16:10 | Manual Inspection
Modal Components
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-RES-MOD-001 | Small Modal | Mobile Size | Test modal < 768px | High | All Modals | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-MOD-002 | Medium Modal | Tablet Size | Test modal 768px-1024px | High | All Modals | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-MOD-003 | Large Modal | Desktop Size | Test modal > 1024px | High | All Modals | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-MOD-004 | Form Layout | Form Response | Test form layouts | High | All Forms | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-MOD-005 | Scroll Behavior | Modal Scroll | Test scroll handling | High | All Modals | Testing Complete | 2024-11-27 16:10 | Manual Inspection
Content Components
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-RES-CONT-001 | Tables | Mobile Tables | Test table responsiveness < 768px | High | All Tables | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-CONT-002 | Images | Image Scaling | Test image responsiveness | High | All Images | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-CONT-003 | Text Flow | Text Wrapping | Test text flow on resize | High | All Components | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-CONT-004 | Navigation | Nav Collapse | Test navigation collapse | High | Header.js, Sidebar.js | Testing Complete | 2024-11-27 16:10 | Manual Inspection
HOA-RES-CONT-005 | Buttons | Button Sizing | Test button responsiveness | High | All Components | Testing Complete | 2024-11-27 16:10 | Manual Inspection

## Security
Authentication Security
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SEC-AUTH-001 | Token Validation | Token Check | Test token validation | High | AuthContext.js, apiService.js | TESTING COMPLETE | 2024-11-30 22:53 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-AUTH-002 | Session Security | Session Check | Test session security | High | AuthContext.js | TESTING COMPLETE | 2024-11-30 22:53 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-AUTH-003 | Password Security | Password Rules | Test password security | High | Login.js, RegistrationModal.js | TESTING COMPLETE | 2024-11-30 22:53 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-AUTH-004 | Access Control | Route Protection | Test route protection | High | ProtectedRoute.js | TESTING COMPLETE | 2024-11-30 22:53 | Manual Testing using HOA Management System Security Test Plan
Data Security
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SEC-DATA-001 | Input Validation | XSS Prevention | Test input sanitization | High | All Forms | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-DATA-002 | SQL Protection | SQL Injection | Test SQL protection | High | apiService.js | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-DATA-003 | File Security | Upload Security | Test file security | High | UploadDocumentModal.js | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-DATA-004 | Data Privacy | Data Protection | Test data privacy | High | All Components | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
API Security
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SEC-API-001 | Request Security | Request Validation | Test API security | High | apiService.js | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-API-002 | Response Security | Response Handling | Test response security | High | apiService.js | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-API-003 | Error Security | Error Handling | Test error security | High | apiService.js | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan
HOA-SEC-API-004 | Rate Limiting | Rate Protection | Test rate limiting | High | apiService.js | TESTING COMPLETE | 2024-11-30 23:06 | Manual Testing using HOA Management System Security Test Plan

## System
Integration Tests
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SYS-INT-001 | Authentication | Login Flow | Test complete login process | High | All Auth Files | TESTING COMPLETE | 2024-11-30 23:08 | Covered by integration test. Duplicate
HOA-SYS-INT-002 | Payments | Payment Flow | Test end-to-end payment | High | All Payment Files | TESTING COMPLETE | 2024-11-30 23:08 | Covered by integration test. Duplicate
HOA-SYS-INT-003 | Documents | Document Flow | Test document management | High | All Document Files | TESTING COMPLETE | 2024-11-30 23:08 | Covered by integration test. Duplicate
HOA-SYS-INT-004 | Messages | Message Flow | Test messaging system | High | All Message Files | TESTING COMPLETE | 2024-11-30 23:08 | Covered by integration test. Duplicate
HOA-SYS-INT-005 | Surveys | Survey Flow | Test survey creation/response | High | All Survey Files | TESTING COMPLETE | 2024-11-30 23:08 | Covered by integration test. Duplicate
Cross-browser Tests
Test ID | Component | Requirement | Test Case Description | Priority | Related Files | Status | Last Tested | Method
HOA-SYS-BRW-001 | Chrome | Chrome Support | Test Chrome compatibility | High | All Components | TESTING COMPLETE |  | Tested constantly with multiple browsers open for back and forth between members
HOA-SYS-BRW-002 | Firefox | Firefox Support | Test Firefox compatibility | High | All Components | TESTING COMPLETE |  | Tested constantly with multiple browsers open for back and forth between members
HOA-SYS-BRW-003 | Safari | Safari Support | Test Safari compatibility | High | All Components | TESTING COMPLETE |  | Tested constantly with multiple browsers open for back and forth between members
HOA-SYS-BRW-004 | Edge | Edge Support | Test Edge compatibility | High | All Components | TESTING COMPLETE |  | Tested constantly with multiple browsers open for back and forth between members
HOA-SYS-BRW-005 | Mobile Browser | Mobile Support | Test mobile browsers | High | All Components | TESTING COMPLETE |  | DID NOT GO LIVE, SO TESTING DID NOT TAKE PLACE IN A MOBILE ONLY BROWSER